## Hoja1
Date: | 2026-01-10 | [19 empty] | Color | Range
[21 empty] | TIME OK | 0 TO 7 DAYS AFTER PI DATE
[21 empty] | CHECK | 7 TO 14 DAYS AFTER PI DATE
Status | Production
Reference TL | IMP0005363-2026
CLAC number | CLAC1567
QTY and type Of containers: | 2x40HQ
Line | CLAC number | Partial | CODE | product | QTY/CTN | TOTAL CTN | CBM/CTN | GW/CTN | TOTAL CBM | TOTAL WEIGHT | PI CONFIRM DATE | PI DELIVERY DATE | artwork confirm Date (Production start date) | Production days | Estimated date after start production | Production report | OK date production report | Loading report | Date order is ready | DELAY according PI | STATUS | COMMENTS ADA | Date of commets | COMMENTS KARLA | Date of commets
1 | CLAC1567 |  | 707091 | SILICONA BARRA DELG OVE 800GR (71 APRX) | 24 | 1000 | 0.285 | 29.2 | 285 | 29200 | 2025-12-29 | 2026-01-08 | 2025-12-31 | 10 | 2026-01-10 | 2025-12-15 |  | 2025-12-17 | 2025-12-10 | 29 | TIME OK | Insufficient materials, 3 fewer boxes. Next shipment scheduled | 2025-12-16
[6 empty] | 1000 |  |  | 285 | 29200
Formulas:
PI DELIVERY DATE = [PI CONFIRM DATE]+[Production days]
Estimated date after start production = [Production days]+N13